## Sheet1
Nerd Girls Sping 2004 Schedule
Category | Task | People Involved | Deadline | Completed?
Batteries | Pick battery type | Asmaa, Rick, Allison | 2004-02-09
Human Factors | Find Max Force on | Mandy | 2004-02-11
steering wheel.
Steering | Find coefficient of | Teren, Becky | 2004-02-18
friction and pick steering
technology
Body Design | Put in CFD program, find | Emily R., Lisa | 2004-02-25
drag coeff. By hand, compare
dims. To Umass car
Sensing Equipment | Tachometer etc. functional and | Sharon | 2004-03-04
wired
Microcontroller | PIC communication, assemble | Laurel | 2004-03-04
breadboard, LCD system
prototype
Lights | Wire up flasher, horn windshield | Emily M. | 2004-03-04
wipers, etc.
Frame | Design frame, backbone first | Allison, Stuart | 2004-03-17
Wheel Assembly | Design wheel assembly and | Laura, Becky, Teren, | 2004-03-24
| suspension | Andrew